Registered Office - 1001A, B Wing, 10th Floor, ‘The Capital’, Bandra Kurla Complex, Bandra (E), Mumbai - 400 051

Corrigendum-1

This is with reference to NPCI’s “RFP for Selection of End-To-End Engineering, Procurement, Construction of deck slab over the Diesel Generator beds & over Rain Water Harvesting area at Siruseri, Chennai.”– NPCI/2024-25/DC/042 dated 18.12.2024. The prospective bidders may please note the following changes:

| S. No | Document reference | Page No | Clause No | Description | Clarification Sought | Additional if any | Clarified by NPCI |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | RFP | 23 | Bid evaluation process | Bid evaluation | We request selection criteria based on QCBS - 80% on Technical & 20% on Financial |  | Technical Scoring cut off is at 70% and those who score above are selected for commercial opening. Hence technically qualified Bidders are only allowed to participate in the next stage of evaluation. |
| 2 | General |  |  | General | Request an estimated project cost |  | Approximately Rs 3 Cr. |
| 3 | General |  |  | General | Pls clarify whether TEFS is already carried out. If so, request you to share the details. |  | With the advancement of additional DC requirement, it is required to increase the capacity of DGs for power backup. Bidders may take note that the site is a completely operational and all the DGs are required for the purpose of power backup. |
| 4 | RFP | 8 | Section 1 | Bid schedule & address | We request you to Waive Bid Security Fee (INR 5,00,000) |  | EMD has been reduced to Rs 2 Lac. This shall be payable through Bank Guarantee only. Validity is for three months and claim period for further four months. |
| 5 | SCC | 10 - 29 | 4.26.1.2 |  | please consider DLP period as 3 months upon completion of project |  | No Change |
| 6 | General |  |  | General | CBRE will only assist the client on documentation works, Client will engage a third-party consultant for obtaining any relevant approvals related to the project, Pls let us know if our understanding is correct |  | Statutory approvals are not required for this project except for shop drawing or any other drawing approval pertaining to the Works from IIT Madras and NPCI. |
| 7 | RFP | 8 | Section 1 | Bid schedule & address | We request an extension for tender submission till 31st January 2025 |  | No Change; 7th Jan 2025 is the date of bid submission. |
| 8 | General |  |  | General | BOCW CESS & GST shall be paid extra by Client |  | Please refer to the terms mentioned in the RFP pertaining to this query. |
| 9 | General |  |  | General | Labour compliances Audits shall be done by CBRE for appointed sub vendors under CBRE. Client required to provide the Principal Employer registration & Form V, if applicable |  | This is in accordance to NPCI requirement. Similarly, if there is any such documents to be submitted by Bidder, the same shall be submitted by Bidder. Please note that there shall not be any extension to the timeline due to this whatsoever. |
| 10 | RFP | 9 | Section 1 & Point No 17 | Bid schedule & address | Request revision on payment terms as indicated below: On Appointment - 20% Against supply of materials at Pro-rata basis claim (Maximum 3 RA Bills) - 60% Against installation works at Pro-rata basis claim (Maximum 2 RA Bills) - 10% Against Handover of Document / Commercial - Closure 5% Retention - 5% |  | The revised payment terms are mentioned separately in the Corrigendum. |
| 11 | GENERAL |  |  | GENERAL |  | Pls share the architectural plan layout and sections | No architectural plan for this project. Section details already available in the tender document |
| 12 | GENERAL |  |  | GENERAL |  | Pls confirm Loading as per IS Code & Design as per MBMA Code | Designed by INDIAN INSTITUTE OF TECHNOLOGY MADRAS, GA drawings prepared based on the design |
| 13 | GENERAL |  |  | GENERAL |  | Need site layout with the existing operational building to be provided | The Master Plan layout is shared in the Corrigendum accordingly. |
| 14 | RFP | Pg 9 of 57 | 11 | Bid Purchase Cost | INR 17,700/- (Indian Rupees Seventeen Thousand Seven Hundred only) (INR 15,000/- plus GST @18 %) | ok | No Comments |
| 15 | RFP | Pg 9 of 57 | 11 | Bid Security | INR 5,00,000/- (Indian Rupees Five Lacs Only)- EMD | Request you to waive off | EMD has been reduced to Rs 2 Lac. This shall be payable through Bank Guarantee only. Validity is for three months and claim period for further four months. |
| 16 | RFP | Pg 9 of 57 | 14 | Scheduled time of Completion | Within three (3) months from the date of issue of Purchase Order (PO) or Letter of Intent (LOI) (whichever is earlier) | To be discussed as per point no 8 below | Period of completion stands unchanged. Three months from the date of issuance of LOI or PO whichever is earlier. |
| 17 | RFP | Pg 9 of 57 | 17 | Schedule of Payment |  | To be discussed | The revised payment terms are mentioned separately in the Corrigendum. |
| 18 | RFP | Pg 9 of 57 | 18 | Performance Bank Guarantee (PBG) | The successful bidder shall submit the PBG at 10% of the PO value with NPCI till the project completion period four (4) months with a claim period of six (6) months (total ten (10) months) as per SUB-CLAUSE 5.1.25 of GCC | Request you to waive off . Project completion was mentioned as 3 months in schedule time of completion. Pls confirm the project duration. | Please note that PBG shall be valid for 3 (three) months from the date of issuance of PO, with a claim period of 6 (six) months from the date of expiry of the validity period of the Bank Guarantee (BG), as per statutory provisions in force. |
| 19 | RFP | Pg 9 of 57 | 19 | Penalty/ Liquidated Damages | The Bidder failing to achieve the project schedule shall pay to NPCI an amount equivalent to 0.5% of contract value per week or part thereof subject to maximum of 5% of the total PO value as liquidated damages as per Section 7.8 of GCC. | ok | No change |
| 20 | RFP | Pg 14 of 57 |  |  | The project duration is envisaged to be total three (3) months (i.e., 2 ½ (two and half) months of construction stage and 0.5 (Half) months of post construction stage and HOTO). The final manpower deployment schedule shall be finalized with the successful Bidder. | Project completion is mentioned as 3 months in schedule time of completion. And mentioned as 4 months in PBG clause. Pls confirm the project duration. | - Period of completion stands unchanged. Three months from the date of issuance of LOI or PO whichever is earlier. - PBG shall be valid for 3 (three) months from the date of issuance of PO, with a claim period of 6 (six) months from the date of expiry of the validity period of the Bank Guarantee (BG), as per statutory provisions in force. |
| 21 | RFP | Pg 14 of 57 |  |  | In addition to that, cover slab over the Rain Water Harvesting Pit, which going to utilize for covered two wheeler parking to increase the parking space in the premises. | Pls provide the drawing | Parking covering is not in the scope of works, |
| 22 | RFP | Pg 18 of 57 | Section 5 -B. Preparation of Bid | Earnest Money Deposit (EMD) | The Bidder is required to submit EMD for an amount of INR Five (5) Lac only by way of Bank Guarantee from a scheduled commercial bank valid for four (4) months, with a claim period of six (6) months (total ten (10) months) after the expiry of validity of the Bank Guarantee as per the statutory provisions in this regard, as per format in Annexure A2. | Request you to waive off . | EMD has been reduced to Rs 2 Lac. This shall be payable through Bank Guarantee only. Validity is for three months and claim period for further four months. |
| 23 | RFP | Pg 19 of 57 | Section 5 -B. Preparation of Bid | Period of Validity of Bids | Bids shall remain valid for a period of six months after the date of bid opening as mentioned in Section 1 or as may be extended from time to time. NPCI reserves the right to reject a bid valid for a period shorter than six months as non-responsive, without any correspondence. | ok | No Comments |
| 24 | RFP | Pg 25 of 57 | 6.6 | Delivery Schedule | Delivery Schedule – 24 Months or till successful completion of HOTO, whichever is later, form the date of issuance of Purchase Order as per Notification of Award / Purchase Order. | Clause not clear to be discussed | Period of completion stands unchanged. Three months from the date of issuance of LOI or PO whichever is earlier. |
| 25 | RFP | Pg 25 of 57 | 6.7 | Price Escalation | Price shall remain fixed for a period of 24 Months from the date of Notification of award / 1st Purchase Order. There shall be no increase in price for any reason whatsoever and therefore no request for any escalation of the cost / price shall be entertained. | Price validity is mentioned as 6 months in period of validity of Bids in point no 13 | Period of validity of the Bid is for twelve (12) month from the date of issuance of PO or LOI whichever is earlier. Rest of the clauses remain unchanged. |
| 26 | RFP | Pg 26 of 57 | 6.8 | Payment Terms |  | as per the point no 7 | The revised payment terms are mentioned separately in the Corrigendum. |
|  |  |  |  |  | Payment shall be made within 30 working days of submission of acceptance of invoice along with all necessary supporting for payment processing and the same shall be subject to tax deductions at prevailing rates |  |  |
| 27 | RFP | Pg 39of 57 |  | Annexure B - Bid Offer Form (without Price) (B | We agree that the bid shall remain valid for twelve (12) months after the date of bid opening. | same as point no 13 | Period of validity of the Bid is for twelve (12) month from the date of issuance of PO or LOI whichever is earlier. Rest of the clauses remain unchanged. |
| 28 | GCC | Pg 6of 124 | 1. GENERAL CONDITIONS |  | m. "Contract Period" means the period of 4 (four) months starting from the Commencement Date. | ok | Contract period is three months from the date of acceptance of PO/LOI |
| 29 | GCC | Pg 21 of 124 | 5.2 | Water Supply and Electric power for construction | Contractor scope | power and water to be provided by client | Temporary power and construction water is under Bidder scope only. |
| 30 | GCC | Pg 22 of 124 | 5.4 |  | Demolition and clearance | Please define scope of works | Please refer to the BOQ for further information on Demolition and Clearance. |
| 31 | GCC | Pg 27 of 124 | 5.7 | Performance bank guarantee | The Successful bidder shall submit a Performance Bank Guarantee (PBG) equal to 10% of contract price (exclusive of taxes), within 10 (Ten) working days of receipt of the LOI or Purchase Order (whichever is earlier) which shall be valid for 4 (Four) months, with a claim period of 12 (Twelve) months from the date of expiry of the validity period of the Bank Guarantee (BG), as per statutory provisions in force. In case the successful bidder is not in a position to submit the PBG for any reason, CLIENT is entitled to withhold an equivalent amount from the first payment due under the Contract Agreemen | Request you to waive off | No change. Please note that PBG shall be valid for 3 (three) months from the date of issuance of PO, with a claim period of 6 (six) months from the date of expiry of the validity period of the Bank Guarantee (BG), as per statutory provisions in force. |
| 32 | GCC | Pg 31 of 127 | 5.12 | Project Schedule | Project Schedule a. Date of award/zero date shall be the date of letter of intent (LOI/LOA/PO), any other form of intent to award or the work order whichever is earlier. b. Start date: 7 days from the date of award which should be mentioned as mobilization period. c. Completion period of the project shall be four (4) months (from the date of award of Contractor through Letter of Award or Purchase Order whichever is earlier. This includes the time taken for approval from IIT Madras for shop drawings or any other drawings. d. The Contractor shall submit a Project Schedule within 5 (Five) days of receipt of the letter of Intent/PO, this shall be prepared &, the Contractor shall also submit mitigation programme whenever previous programme is inconsistent with actual progress on site. The Contractor may present proposals which leads to completion of Project in shortened period. | Schedule shall be discussed. | All clauses mentioned remain unchanged except period of completion remains at three months from the date of issuance of LOI or PO whichever is earlier. |
| 33 | GCC | Pg 34 of 127 | 5.12 |  |  |  | - Supply of 100 % steel elements such as ISMB, ISHB, Buildup sections as per approved shop drawings – 10th Mar 25 - Upon 100% completion of works as per approved shop drawings for DG 1,2 & RWH works includes staircase for DG 1 & 2, Plastering & finishings – 31st Mar 25 |
| 34 | GCC | Pg55 of 127 | 7.4 | Time for completion | The whole of the Package works as per the technical Specifications & Drawings for the Completion of Milestones to be completed in all respects shall be completed; each contract will have specific timelines none of which will exceed 3 (three) months from the date of final sign-off on the Final mutually accepted Price, BOQ and mutually agreed Terms through Letter of Award or Purchase Order whichever is earlier plus 15 days for the completion of snag list | Pls confirm whether the schedule is 3 months or 4 months | Period of completion stands unchanged. Three months from the date of issuance of LOI or PO whichever is earlier. |
| 35 | GCC | Pg 68 of 127 | 12.1 |  | Certificates and Payment |  |  |
|  |  |  |  |  |  | shall be discussed | The revised payment terms are mentioned separately in the Corrigendum 1. |
| 36 | SCC | Pg 10 of 29 | 4.26.1 |  | The payments shall be made in the following manner: |  |  |
|  |  | Pg 10 of 29 | 4.26.1.2 |  | The Final Bill amount shall be released after completion of work, and retention money retained from the running bills shall be retained for a period of 24 months defect liability period. The Contractor shall submit its running bills for payment concerning work executed or materials delivered on the Site, will be certified by the Project Manager for payment as noted in Tender/RFP Annexure.+F7 | DLP is mentioned as 12 months in GCC12.3.4 - Pg 71 of 124. We are agreeing for 12 month DLP Only. | DLP is from date of completion of works and issuance of substantial completion certificate issued by NPCI. Rest of the clauses remain unchanged. |
| 37 | SCC | Pg 11 of 29 | 6 | PENALTY/LIQUIDATED DAMAGES | If the successful bidder does not deliver the project within the agreed delivery schedule, or such authorized extension of delivery period as may be permitted in writing by CLIENT, CLIENT shall impose a penalty as given below: 0.5% of the Contract Price for each weeks delay subject to maximum of 5% (Five Per Cent) of the Contract Price without prejudice to any other right or remedy available under the contract agreement. In case the penalty exceeds 5% (Five Per Cent), CLIENT reserves the right to terminate the Contract Agreement, forfeit any or all bank guarantees submitted to CLIENT. | ok | No Change. |
| 38 | SCC | Pg 11 of 29 | 7 | BILL CYCLE OF PAYMENTS. | Milestone running bills with complete supporting measurement sheets & supporting documents such as manufacturing test report(MTR)/NABL test reports, technical data sheet (TDS), test reports by Delivery challan, etc. shall be submitted by the Contractor and shall be certified for quality of work done and assessed quantities of Work completed. Assessment of Project Manager/Auditor shall be final. Milestone RA bills shall be raised based on the achievement of the milestones as mentioned in the Project Schedule. Only one milestone bill per month will be allowed. Payment for RA bills shall be made within 30 (Thirty) days after the final acceptance of the bill Final milestone bill will be certified by the Project Manager after verification by CLIENT’s appointment consultants namely Architects, CMC etc of all the required details and submission of as built drawings, duly checked milestone/final measurements and all other documents as required to be submitted by the Contractor, as stipulated/listed in thisContract. Payment for final bill shall be made 60 after the receipt of the bill after the final acceptance of the bill | This short term project , we need payment within 7 days from the date of certification of bill | No Change. Basis the feedback received from Bidders during the Pre Bid meeting, considering the tenure of the project being three months, NPCI shall endeavour to release payment at the earliest. However Bidder must ensure that all documentation required by our Internal teams are provided for clearance of invoices shall be submitted to enable faster settlement of payments. |
| 39 | SCC | Pg 24 of 29 | 33 | VALUATION OF VARIATIONS | 33.5 The Contractor shall be bound to carry out any extra items of work, and wherever possible, the rate for extra items shall be derived from the rate already quoted. It is further clarified that for all such authorized extra items where rates cannot be derived from bid, the Contractor shall submit rates supported by rate analysis worked on the “market rate basis” (including Labour , Material , wastages , constant shall be of CPWD, if available in CPWD Rate analysis and Rates shall be based on Present market Rates), for Landed cost (material, labour, hire/ running charges of equipment, transportation and wastages) including design and drawings, plus 10% (Ten Per Cent) towards establishment charges, Contractor ’s overheads and profit. | Request for plus 20% (Twenty PerCent) towards establishment charges, Contractor ’s overheads and profit. | No Change. |
| 40 | SCC | Pg 25 of 29 | 33.5 |  | Rate for extra items (ready-made) directly bought by the Contractor shall be allowed with profits @ 10% (Ten Per Cent) of the cost. | plus 20% (Twenty PerCent). Suggested | No Change. |
| 41 | Deckslab boq |  |  | Blockwork and Platering | Blockwork and plastering details for the Handrail required |  |  |
|  |  |  |  |  |  | Blockwork item not in Boq. | Consider as Upstand beam to be constructed with RCC to avoid water leakage. Bidder to provide this in the shop drawing for approval. |
| 42 | Deckslab boq | 3 | 3.02 | Structural Staircase | Designing, Providing, fabricating and erecting Structural steel members in position at all levels and at all heights as specified in the drawings made out of standard MS sections / Built up section/ISHB/ISMB & tubular section conforming to IS 226/2062/800. Cost to include fabricating necessary Gusset Plates, insert plates,pedestal bolts,softners,Channels,beams,angles,tees,rods,chequered plates, hold fasts Stiffener plates, Brackets, Bolts, Cleats, seatings etc., to the required size, shape, alignment etc, as per the drawings. Cost to include fillet welding,butt welding of members using structural steel welding electrodes and splices as per IS 814/816/817, a coat of anti corrosive primer (non flammable) to the exposed surfaces, testing as per IS 7307 (PART 1), necessary equipment's, tools and tackles, staging, scaffolding required etc., complete. for roof, wall sides, floors etc., including 1 coat of min. 75 micron approved metal primer zinc chromite and two coats epoxy paint of approved colour by the architect/Project Manager/Client. Making of structural staircase with handrails which enables to access DG sets located at all floor levels. | Drawing is required | - Shop Drawings to be prepared by Bidder based on site conditions & which should be wetted & approved by IITM madras & NPCI. This should include all foundation details and other joineries. - The pedestal reinforcement details for DG 1 and 2 are enclosed for your information and necessary action. Please note that quantity of reinforcement and other works to be considered in the BOQ under relevant sections. |
| 43 | Deckslab boq | 3 | E | REMOVING AND DEMOLISHING OF EXISTING PEDESTAL | All the existing Pedestals shall be demolished upto 1 meter height from the base slab and disposed and the debrises will be disposed to the authorised local areas. | Qty is mentioned as Lumpsum, shall the qty be given | No Change. Bidders are requested to visit the site to evaluate the quantities. |
| 44 | Deckslab boq | 3 | E | REMOVING AND DEMOLISHING OF EXISTING PEDESTAL | Existing Fence shall be removed before the work commence and it will be refixed in the same position after the completion of all works | Qty is mentioned as Lumpsum, shall the qty be given | No Change. Bidders are requested to visit the site to evaluate the quantities. |
| 45 | RWH Boq |  |  | RWH Boq |  | Drawing is required for the scope of works | Will share the GA drawings |
| 45 |  |  |  |  |  | As this is BOQ based contract we request you to give us GA drawings and Stad files to proceed with Shop drawings | Will share the GA drawings |
| 47 |  |  |  |  |  | Mode of measurement of bills for Steel is it Tekla Weight or Kanta Weight or Stad Model Weight | The mode of measurement shall be basis the final shop drawing prepared with detailed quantities. Shop drawing to be approved by IIT Madras. |
| 48 |  |  |  |  |  | Is Site welding permitted on this project | Site welding is allowed. However safety precautions to be taken for completely operational DG Bed 1 and 2. Cost of all safety precautions to be borne by Bidder. |
| 49 | RFP | 25 of 57 | 6.7 Price Escalation | Price shall remain fixed for a period of 24 Months from the date of Notification of award / 1st Purchase Order. | Requesting you to kindly consider the price validity period shall be 12 months since the price of Steel is varying time to time |  | Period of validity of the Bid is for twelve (12) months from the date of issuance of PO or LOI whichever is earlier. Rest of the clauses remain unchanged. |
| 50 | RFP | 52 of 57 | Key Equipment availability | Attach Copy of purchased Invoices for each of the proposed Equipment’s as per the table above, Registration certificates for applicable machinery | Required details of the machineries will be provided before start of the work |  | The list of machineries in tentative not exhaustive. The selected Bidder to ensure requisite machineries are made available at the site during installation. |
| 51 | GCC | 24 of 127 | 5.5.1 Vehicular movements and temporary roads | No vehicle other than those specifically allowed by the Project Manager shall be permitted in the Site | Dedicated way to be provided for the Construction vehicle movement |  | This shall be shared with the selected Bidder. |
| 52 | GCC | 54 of 127 | 7.1 Commencement of Work | The contractor shall commence the work on site within 4 days from the date of NPCI's written work order to commence the work | It requires minimum 7 days |  | 7 days from date of PO. However the period of completion shall remain unchanged. |
| 53 | GCC | 57 of 127 | 7.8 Liquidated damages for delay | Contractor failing to achieve the project schedule shall pay to NPCI an amount equivalent to 0.5% of the Contract Price for each week’s delay subject to maximum of 5% (Five Per Cent) of the Contract Price | Requesting to limit the percentage to 0.1% till 1% of maximum instead of 0.5% to 5% |  | No Change |

The revised Payment terms are as under:

Mobilization Advance: 10% (subject to submission of APBG) 1. Upon completion of civil structures namely RWH raft foundation with RCC column, DG 1& 2 Pedestal Concrete completion: 15% 2. Upon delivery of steel structures on pro rata basis: 60% 3. Upon completion of all Works: 20% 4. Retention: 5% up to completion of DLP Period of 1 year.

The rest of the terms and conditions as set out in the RFP and other related documents remain unchanged.